## Sheet1
Sprint | Task | Subtask | Member | Duration | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Sprint 1 | Internal revision | Review past deliverables | Team | 1 | Done
Sprint 1 | Cleaning pipeline | Design KNN+LR cleaner | Khoa | 1 | Done
Sprint 1 | Data Collection | Drive sample and logging | Dale | 12 | On going
Sprint 1 | Driver behaviour | Initial K-Means clustering | Barsat | 1 | Done
Sprint 1 | PM Research | DL/RL literature review & plan | Khoa | 1 | Done
Sprint 1 | PM Prototype | Hybrid scoring + thresholds + Exposure + TCN-AE | Khoa | 1 | Done
Sprint 1 | Infrastructure | Add MongoDB export endpoint | Khoa | 1 | Done
Sprint 1 | PM Prototype | Constants documentation & Colab handover | Khoa | 1 | Done
Sprint 1 | Notification | Early researches of efficiency alerts | D, B, S | 1 | On going
Sprint 2 | Algorithms | Early researches of cost-efficienct algorithms | D, B, S |  | On going
Sprint 3 | Model | Early researches of cost-efficienct modelling | D, B, S |  | On going
Sprint 2 | Driver Behaviour | Stabilise K-Means clustering | Barsat | 2 | Planned
Sprint 2 | Data Collection | Controlled baseline driving data collection | Dale | 2 | Planned
Sprint 2 | Infrastructure | Mongo→API→UI wiring | Khoa | 2 | Planned
Sprint 2 | Metrics | Define wear/tear & fuel metrics | Sadman | 1 | Planned
Sprint 2 | Algorithms | Cost-efficienct algorithms | D, S | 4 | Planned
Sprint 2 | Model | Cost-efficienct models | B, K | 4 | Planned
Sprint 2 | Notification | Webhook service & thresholds | Sadman | 1 | Planned
Sprint 2 | Validation | Criteria & baseline eval framework | Barsat | 1 | Planned
Sprint 3 | Validation | Validate subsystem maps & weights | Khoa | 1 | Planned
Sprint 3 | Infrastructure | Pipeline monitoring & hardening | Sadman | 1 | Planned
Sprint 3 | Notification | Dashboard notification pane (+LLM if applicable) | Khoa | 1 | Planned
Sprint 3 | Infrastructure | Clustering + cost model integration | Dale | 1 | Planned
Sprint 3 | Infrastructure | Pi batch uploader improvements | Sadman | 1 | Planned
Sprint 3 | Benchmarking | Compare vs industry references | Barsat | 1 | Planned
Sprint 3 | Driver Notification | Subsystem-specific cost modelling | Dale | 1 | Planned
Sprint 3 | Driver Notification | LLM explanation tuning & UX design | Khoa | 1 | Planned
Sprint 3 | Infrastructure | Notification API → Dashboard binding | Sadman | 1 | Planned
Sprint 3 | Metrics | Expand scoring weights library | Barsat | 1 | Planned
Sprint 3 | Integration | End-to-end pipeline (Cleaner→Cluster→Notif) | Team | 2 | Planned
Sprint 3 | Evaluation | Closed-loop validation with synthetic stress data | S, K | 2 | Planned
Sprint 3 | Edge | On-device inference feasibility (Pi) | B, D | 2 | Planned
Sprint 4 | Driver Notification | Final notification UI (A/B messaging) | Khoa | 2 | Planned
Sprint 4 | Cost Analysis | Fuel savings vs baseline | Dale | 2 | Planned
Sprint 4 | Infra | Notification reliability tests | Sadman | 2 | Planned
Sprint 4 | Benchmarking | Industry validation report | Barsat | 2 | Planned
Sprint 4 | Client Demo | Full pipeline showcase | Team | 2 | Planned
Sprint 4 | Wrap-Up | Documentation & Final Report | Team | 2 | Planned